## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team and Freshman Seminar acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions, cross-team testing, and Freshman Seminar testing.
Team Name | term 2181-swen-261-11-d
Testing Team Name | fill in when doing cross-team or Freshman Seminar testing

## Test Plan
User Story | Acceptance Criterion | Sprint 1 | Tester initials; date; comments (required if test failed) | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Player I want to sign-in so that I can play a game of checkers. | Given that I have not yet signed in when I see the Home page then I must see a means to sign-in. (such as a link or button) | Pass | JK 10/20 | Pass | SQ 10/26
| Given that I am not signed-in when I do click on the sign-in link then I expect to be taken to the Signin page, with a means to enter a player name. | Pass | SF 10/21 | Pass | SQ 10/26
| Given that no one else is using my name when I enter my name in the sign-in form and click the Sign-in button then I expect system to reserve my name and navigate back to the Home page. | Pass | JK 10/20 | Pass | SQ 10/26
| Given that no one else is using my name when I enter a name with a double quote (`"`) then I expect the system to reject this name and return the sign-in form. (Note: double quote is not a valid character in a Player's name.) | Pass | SF 10/21 | Pass | SQ 10/26
| Given that someone else with my name has signed-in when I enter my name in the sign-in form then I expect the system to reject my sign-in and return the sign-in form. I can then choose a different user name. | Pass | NS 10/21 | Pass | SQ 10/26
| Given that I have signed in when I see the Home page then I must see a means to sign-out. (such as a link or button) Thus the sign-in and sign-out links need to alternate and never been seen together or not at all. | Pass | JK 10/20 | Pass | SQ 10/26
| Given that I am signed-in when I click on the sign-out link then I expect the system to sign me out, release my name for use by other users, and then return me to the Home page. | Pass | NS 10/21 | Pass | SQ 10/26
| Given that I am signed-in when I navigate to the Home page then I expect to see a list of all other signed-in players. (NOTE: in the next story you will use this list to pick opponents for checkers games.) | Pass | JK 10/20 | Pass | SQ 10/26
| Given that I am not signed-in when I navigate to the Home page then I expect to see a message of how many players are signed-in but not a list of them (for privacy reasons). | Pass | SF 10/21 | Pass | SQ 10/26
As a Player I want to start a game so that I can play checkers with an opponent. | Given that I'm signed in when I view the Home page then I can start a game by selecting a player listed on the Home page. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given that the player I selected isn't yet in a game when I select that player then the system will begin a checkers game and assign me as the starting (Red) player and my opponent as the White player. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given that the player I selected is already in a game when I select that player then the system will return me to the Home page with an error message. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given that I'm waiting for a game when another player selects a game with me then the system will automatically send me to the Game View from the Home page. NOTE: the `home.ftl` HTML includes a `<meta>` tag that tells the browser to refresh the game every 5 seconds; thus you need to update the `GetHomeRoute` controller to handle the situation when a player is assigned a game. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given a valid, initial game board when I drag a piece to a white space then the piece should not be droppable. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given a valid, initial game board when I drag a piece to an occupied space then the piece should not be droppable. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given a valid, initial game board when I drag a piece to an open space then the piece should be droppable. NOTE: In this Story the drop action should not do anything; piece movement will be the focus of future stories. | Pass | 10/24 SQ | Pass | SQ 10/26
| Given a valid, initial game board when I view the board in the browser then my pieces are oriented on the bottom of the board grid just like I would see the board if I were playing in the physical world. | Pass | 10/24 SQ | Pass | SQ 10/26
As a Player I want to move to an empty space so that I can move my pieces around the board. | Given I make a valid move when my turn completes then it's my opponents turn |  | N/A | Pass | ZM 10/26
| Given a move is invalid when my piece is returned then I expect to be able to move again |  | N/A | Pass | ZM 10/26
| Given I make a valid move when my turn completes then I shouldn't be able to move again |  | N/A | Pass | ZM 10/26
| Given a piece is moved when the requested space is occupied then I expect to have my piece returned. |  | N/A | Pass | ZM 10/26
| Given the move is valid when I drag a piece to a space then I expect my piece to move and occupy that space. |  | N/A | Pass | ZM 10/26
As a Player I want to jump over one of my enemy's pieces so that I can take their piece. | Given It is my turn when there is an enemy piece diagonal to my piece then I expect to be able to jump over that piece. |  | N/A | Pass | NS 11/17
As a Player I want to be forced to take a move if available so that I won't miss my full turn. | Given It is my turn when I have an opportunity to jump then I expect the game to make me jump. |  | N/A | Pass | NS 11/17
As a Player I want to take the enemies piece so that I can win the game. | Given that I jump over an opponents piece when I make a move then I except to take that opponent's piece. |  | N/A | Pass | NS 11/17
As a Player I want to jump multiple of the enemy's pieces at a time so that I can win faster. | Given a user jumps a piece when there is another piece eligible to be jumped then the player will be able to execute multiple jumps |  | N/A | Pass | NS 11/17
As a PLAYER I want to PLAY WITH ILLEGAL MOVES DISABLED so that MY OPPONENT AND I CANNOT CHEAT. | Given a move is illegal when a player attempts to make that move then I expect the game to reject the move. |  | N/A | Pass | JK 10/29
| Given a move is illegal when a player attempts to make that move then I expect the game to notify the player that the move was illegal. |  | N/A | Pass | JK 10/29
As a PLAYER I want to BE NOTIFIED WHEN THE GAME IS OVER so that I DO NOT HAVE TO MANUALLY END THE GAME WHEN I WIN OR LOSE. | Given I am playing a Game when I collect all of the other players pieces then I expect to be notified that I won the game. |  | N/A | Pass | NS 10/28
| Given I am playing a Game when my opponent resigns from the game then I expect to be notified that I won the game. |  | N/A | Pass | NS 10/28
As a PLAYER I want to BE FORCED TO PLAY IN TURN so that MY OPPONENT AND I HAVE AN EQUAL NUMBER OF TURNS. | Given it is not my turn when I press the backup button then I expect nothing to happen. |  | N/A | Pass | ZM 10/30
| Given it is not my turn when I press the submit turn button then I expect nothing to happen. |  | N/A | Pass | ZM 10/30
| Given it is not my turn when I try to move a piece then I expect to not be able to move that piece. |  | N/A | Pass | ZM 10/30
As a PLAYER I want to LET THE RED PLAYER MOVE FIRST so that THE GAMES I PLAY ARE CONSISTENT . | Given I have started a game when I am the white player then I expect to NOT go first. |  | N/A | Pass | SF 10/31
| Given I have started a game when I am the red player then I expect to go first. |  | N/A | Pass | SF 10/31
As a Player I want to be able to sign out so that nobody can play checkers against my account or on my account. | Given a user clicks sign out when they are playing a game then that user's opponent from the game will be returned to the home page. |  | N/A | Pass | SQ 11/2
| Given a user clicks sign out when they are playing a game then another user will be able to sign in. |  | N/A | Pass | SQ 11/2
| Given a user clicks sign out when they are playing a game then the user will be returned to the home screen. |  | N/A | Pass | SQ 11/2
| Given a user clicks sign out when they are playing a game then the user will be removed from the player lobby. |  | N/A | Pass | SQ 11/2
| Given a user clicks sign out when they are playing a game then the user will be removed from the game. |  | N/A | Pass | SQ 11/2
As a Player I want to forfeit the game so that I do not have to play out the game. | Given a player wants to resign when they press the forfeit button then the game will end and the opponent will win. |  | N/A | Pass | SQ 10/31